## Summary
SEI - BBH Integration: Engineering Design Tracker
65 components across 4 zones. Stack: Python (ingestion) + dbt (transformation) + Airflow (orchestration) on OpenShift/Oracle.
One design document per component. 'Custom Build = High' means no framework default covers it - design doc mandatory before code.
By zone
Zone | Components | P1 | High Custom | Not Started | In Design | Approved
1. SEI | 7 | 3 | 0 | 7 | 0 | 0
2. Hub | 29 | 21 | 12 | 29 | 0 | 0
3. Consumers | 7 | 1 | 0 | 7 | 0 | 0
4. OpenShift | 22 | 11 | 1 | 22 | 0 | 0
TOTAL | 65 | 36 | 13 | 65 | 0 | 0
By build track
Technology (contains) | Components | High Custom
Python | 10 | 8
dbt | 10 | 3
Airflow | 10 | 3
Oracle DDL | 4 | 1
Infra | 24 | 0
CI/CD | 3 | 1
Vendor | 3 | 0
Contract | 8 | 0
Note: components spanning two tracks are counted in both.
Key counts
Components marked NEW (in neither source deck) | 28
Components with Custom Build = High | 13
Open architecture decisions | 12

## Components
ID | Zone | Plane / Group | Component | Design Deliverable (what to produce) | Key Design Questions | Depends On | Source | Priority | Technology | Custom Build | Custom Development Scope | Owner | Status | Target Date | Notes
1 | 1. SEI | Source | SWP Platform | Interface spec: domains, entities, extract triggers | Which domains are in scope for phase 1? | - | SEI v5 | P1 | Contract | None | SEI-owned. Specification review only. |  | Not Started
2 | 1. SEI | Source | SWP UI | Access model + SSO handshake spec | Which BBH roles need UI access? | 36 | SEI v5 | P3 | Contract | None | SEI-owned. |  | Not Started
3 | 1. SEI | Source | SWP APIs | API contract: endpoints, auth, rate limits, SLAs | Which consumers use real-time vs batch? | 12 | SEI v5 | P1 | Contract | None | SEI-owned. Consume as published. |  | Not Started
4 | 1. SEI | Source | SWP Loaders | Loader file format + submission/ack contract | Sync or async ack? Failure semantics? | 10, 11 | SEI v5 | P2 | Contract | None | SEI-owned. |  | Not Started
5 | 1. SEI | Source | Extract Generation | File spec: layout, naming, manifest, EOD + intraday cadence | Full snapshot daily, or change-indicator available? | 8 | SEI v5 | P1 | Contract | None | SEI-owned. Ask for hash/change column - biggest volume lever. |  | Not Started
6 | 1. SEI | PS-Orchestration | Orchestration API / Data Ingestion / ODM / Workflows / Config | Outbound orchestration design (SEI-owned, BBH-reviewed) | Is outbound in scope this phase? | 10, 11 | SEI v5 | P3 | Contract | None | SEI-owned. |  | Not Started
7 | 1. SEI | PS-Orchestration | Status Monitoring Dashboard | Status event contract to Integration360 | Does this or Integration360 hold the recon record? | 35 | SEI v5 | P2 | Contract | Low | Event schema agreement; no BBH build. |  | Not Started
8 | 2. Hub | Ingress/Egress | Landing Zone + Transport | Transport design: protocol, auth, dirs, retention, completeness signal | sFTP or object store? Same for EOD and intraday? | 5 | Both (conflict) | P1 | Infra | Low | Managed service + config. Custom only for manifest/completeness check. |  | Not Started
9 | 2. Hub | Ingress/Egress | File Arrival Sensors | Per-file sensor design; start-on-arrival not batch-complete | Manifest-driven or filename pattern? | 8, 18 | NEW | P1 | Airflow | Medium | Custom sensor/deferrable operator per domain. Base sensors do not know your manifest. |  | Not Started
10 | 2. Hub | Ingress/Egress | Outbound Producers | Design for Data Extracts, JSON payloads, Loader File | Which BBH systems are sources? | 43 | SEI v5 | P3 | Python | High | Full custom build: extract, JSON serialisation, loader-file format per SEI spec. |  | Not Started
11 | 2. Hub | Ingress/Egress | Apigee Proxy | Proxy design: submit path + status-return path | Is Apigee a decision or a placeholder? (AD-3) | 10, 35 | SEI v5 | P3 | Vendor/Infra | Low | Proxy config + policies. No application code. |  | Not Started
12 | 2. Hub | Ingress/Egress | API Gateway / Data Plane | Real-time route design, independent of batch | Does intraday run here or on batch? (AD-4) | 3, 42 | BBH V4.2 | P2 | Vendor/Infra | Low | Gateway config, routing, throttling policies. |  | Not Started
13 | 2. Hub | Processing | Python Ingestion Framework | Module design: validation, profiling, metadata capture, RAW load | cx_Oracle vs SQL*Loader vs External Tables? | 8, 14, 23 | SEI v5 | P1 | Python | High | CORE BUILD. Reusable config-driven framework, not 7 scripts. Loader abstraction + audit column injection. |  | Not Started
14 | 2. Hub | Processing | Stage 1 RAW | Physical model: 7 RAW_* tables, 8 audit cols, partitioning, retention | Partition by BUSINESS_DATE? Purge policy? | 13 | SEI v5 | P1 | Oracle DDL | None | DDL + partitioning. No application code. |  | Not Started
15 | 2. Hub | Processing | Stage 2 Enriched (dbt) | 5 STG2_* models, 8 processing steps, tests | Full refresh or incremental per model? | 14, 17, 25 | SEI v5 | P1 | dbt | Medium | Standard dbt models. Custom macros for dedup and latest-record selection. |  | Not Started
16 | 2. Hub | Processing | Gold (dbt) | 2 SCD2 dims + 3 facts; SCD2 and merge logic | Writes to Hub schema or PBDW/IMDS direct? (AD-1) | 15, 26, 60 | SEI v5 only | P1 | dbt | High | dbt snapshot will NOT cover this. Custom incremental SCD2 macro + merge strategy per fact. |  | Not Started
17 | 2. Hub | Processing | Correction Handling | Bitemporal vs merge design, applied across Stage 2 and Gold | One answer both layers. (AD-2) | 15, 16, 21 | Both (conflict) | P1 | dbt | High | No dbt idiom for bitemporal. Custom incremental strategy / macro, written once and reused. |  | Not Started
18 | 2. Hub | Orchestration | Airflow DAG + Per-Domain Fan-out | DAG design: 7 parallel branches, join points, retries | Where do branches legitimately join? | 9, 51, 52 | SEI v5 + NEW | P1 | Airflow | High | Dynamic task mapping over domain config. Not a hand-written static DAG. |  | Not Started
19 | 2. Hub | Orchestration | Dim-before-Fact / dbt Threads | Build-order and concurrency design | Thread count vs Oracle contention ceiling? | 16, 55 | NEW | P2 | Airflow + dbt | Low | Selector config and thread tuning. |  | Not Started
20 | 2. Hub | Orchestration | Intraday Cadence Control | Cadence design and lane assignment | Frequency? Batch pipeline or API route? (AD-4) | 12, 18 | SEI v5 | P1 | Airflow | Medium | Custom scheduling logic; overlap prevention with the EOD run. |  | Not Started
21 | 2. Hub | Orchestration | Replay / Rerun Engine | Replay design from LOAD_ID; scope, idempotency, downstream impact | Replay rewrites Gold in place or appends? (ties to AD-2) | 14, 17, 27 | NEW | P1 | Python + Airflow | High | CORE BUILD. Airflow clear/backfill does NOT undo a Gold merge. Bespoke replay orchestration + idempotency. |  | Not Started
22 | 2. Hub | Orchestration | Partial-Batch Policy | Policy + implementation: halt-all vs per-domain proceed | Can consumers tolerate a partial business date? (AD-5) | 18, 23 | NEW | P1 | Airflow | Medium | Custom branching + trigger rules. Publish-completeness marker per domain. |  | Not Started
23 | 2. Hub | Data Quality | G1 File / Structural Gate | Check set + quarantine design. BLOCKS RAW insert | Which failures are fatal vs warn? | 8, 13, 28 | SEI v5 | P1 | Python | High | Custom validation engine driven by the rule registry. Blocking semantics + quarantine. |  | Not Started
24 | 2. Hub | Data Quality | G2 RAW Profiling Gate | Profiling checks. BLOCKS Stage 2 | Thresholds absolute or vs trailing average? | 14, 28 | SEI v5 | P2 | Airflow + SQL | Medium | Aggregate SQL pushed to Oracle; custom threshold comparison and branch. |  | Not Started
25 | 2. Hub | Data Quality | G3 dbt Tests + Business Rules | Test suite + rule design. BLOCKS Gold | Which rules are dbt tests vs model logic? | 15, 28 | SEI v5 | P1 | dbt | Medium | Generic tests cover basics; custom singular tests + generic test macros for business rules. |  | Not Started
26 | 2. Hub | Data Quality | G4 Tie-out / Control Totals | RAW-to-Gold reconciliation. BLOCKS Gold publish. Per-target | Recount or compare to captured ingest metadata? | 14, 16, 28 | NEW | P1 | Airflow + SQL | High | CORE BUILD. dbt tests cannot do this - it crosses the graph and must gate the publish. |  | Not Started
27 | 2. Hub | Data Quality | G5 Post-Publish Recon | Advisory recon; triggers replay | What auto-triggers a replay vs pages a human? | 16, 21 | SEI v5 | P2 | Airflow + SQL | Medium | Custom recon queries + replay trigger integration. |  | Not Started
28 | 2. Hub | Data Quality | DQ Framework | Rule registry, severity tiers, results store, audited override path | Who can override at 2am, and how is it logged? | 33, 31 | NEW | P1 | Python | High | CORE BUILD. Registry schema, severity model, results store, override API + audit trail. |  | Not Started
29 | 2. Hub | Foundation | Error Handling & Quarantine | Error taxonomy, quarantine store, resubmission path | Quarantine retention and reprocessing route? | 23, 50 | Both | P1 | Python | High | Custom taxonomy + quarantine lifecycle + resubmission path. |  | Not Started
30 | 2. Hub | Foundation | Reconciliation Framework | Recon model: control totals, exception lifecycle | Who owns the recon record? (AD-6) | 26, 27, 35 | Both | P1 | Python | High | Custom recon data model + exception lifecycle + Integration360 publication. |  | Not Started
31 | 2. Hub | Foundation | Audit & Lineage | End-to-end lineage design, evidence retention | Is lineage audit-defensible under AD-2? | 14, 17 | Both | P1 | Python + dbt | Medium | dbt docs covers model lineage only. Custom row-level lineage via LOAD_ID chain. |  | Not Started
32 | 2. Hub | Foundation | Security & Access Control | AuthN/AuthZ model, data classification, masking | Any PII in SWP extracts requiring masking? | 47, 48 | BBH V4.2 | P1 | Infra | Low | Oracle roles/grants + platform controls. Custom only if masking required. |  | Not Started
33 | 2. Hub | Foundation | Metadata & Configuration Store | Config model: rules, thresholds, mappings, schedules | One store, or does SEI keep its own? (risk R1) | 6, 28 | Both | P1 | Oracle DDL + Python | High | CORE BUILD. Everything config-driven depends on this. Build first. |  | Not Started
34 | 2. Hub | Foundation | Observability | Logs, metrics, traces; SLIs and alerting | What are the SLOs for the EOD window? | 64 | BBH V4.2 | P2 | Infra | Low | Standard stack + custom metric emission from Python/Airflow. |  | Not Started
35 | 2. Hub | Foundation | Integration360 | Monitoring, exception mgmt, process tracking, recon | Does it become the system of record? (AD-6) | 7, 30 | Both | P1 | Vendor/BBH | Medium | Existing BBH platform. Custom feed/adapter from the Hub. |  | Not Started
36 | 2. Hub | Foundation | SSO | SSO design to SWP UI | Federation protocol and identity source? | 2 | SEI v5 | P3 | Infra | None | Configuration only. |  | Not Started
37 | 3. Consumers | Consumers | PBDW | Publication design + change control | Direct dbt writes or publish pattern? (AD-1) | 16, 60 | Both | P1 | Oracle DDL + dbt | Medium | Existing tables. Custom publish/swap pattern if AD-1 lands Hub-owned. |  | Not Started
38 | 3. Consumers | Consumers | IMDS Stage -> IMDS | Staging DB + load design from Stage 2 | Missing from BBH deck - confirm it exists | 15 | SEI v5 only | P2 | Oracle DDL + dbt | Medium | New staging schema + load models. |  | Not Started
39 | 3. Consumers | Consumers | Pivotal Database | Feed design from Stage 2 | Absent from SEI 8-component list - scope gap | 15 | BBH V4.2 only | P2 | dbt | Medium | New feed. Not costed in SEI scope. |  | Not Started
40 | 3. Consumers | Consumers | CP DW Canonical Model | Forward-compatibility design only (future) | Keep Stage 2 neutral enough to attach later | 15 | BBH V4.2 (future) | P3 | Design only | None | No build this phase. Design constraint on Stage 2 only. |  | Not Started
41 | 3. Consumers | Consumers | BI / Analytics | Semantic layer + access design | Which of ~1000 consumers land where? | 16 | SEI v5 | P2 | BI tooling | Low | Power BI / Tableau models. Outside the Python/dbt stack. |  | Not Started
42 | 3. Consumers | Consumers | Real-time Consumers | Consumer contract on the API lane | Which use cases justify real-time? | 12 | BBH V4.2 | P2 | Contract | None | Consumer-side build, not Hub. |  | Not Started
43 | 3. Consumers | Consumers | BBH Existing Systems | Impact assessment: front/back office, trade, custody | Which are sources for outbound? | 10 | SEI v5 | P3 | Analysis | None | Assessment only this phase. |  | Not Started
44 | 4. OpenShift | Platform | Projects / Namespaces | Environment topology: dev, test, UAT, prod | Namespace per env, or per env per component? | - | NEW | P1 | Infra | None | Platform config. |  | Not Started
45 | 4. OpenShift | Platform | Container Images | Base image standard: Python, dbt, Airflow | Who owns base image patching cadence? | 57 | NEW | P1 | Infra | Medium | Custom Dockerfiles per runtime; dependency pinning for dbt + cx_Oracle. |  | Not Started
46 | 4. OpenShift | Platform | Registry, Scanning, Signing | Image supply-chain design + promotion policy | What CVE severity blocks promotion? | 45, 57 | NEW | P2 | Infra | None | Tooling config. |  | Not Started
47 | 4. OpenShift | Platform | Service Accounts, RBAC, SCCs | Cluster access model | Least-privilege per workload? | 32 | NEW | P1 | Infra | None | Platform config. |  | Not Started
48 | 4. OpenShift | Platform | Secrets Management | Secrets design: Oracle creds, sFTP keys, API tokens | Vault or sealed secrets? Rotation policy? | 32 | NEW | P1 | Infra | Low | Config + custom secret injection into Airflow connections. |  | Not Started
49 | 4. OpenShift | Platform | Network Policy & Egress | Egress to SEI/Apigee/Oracle; ingress rules | Firewall path to SEI approved? | 8, 11 | NEW | P1 | Infra | None | Network config. Long lead time - start early. |  | Not Started
50 | 4. OpenShift | Platform | Persistent Storage | Volume design: landing, quarantine, dbt artifacts, logs | Capacity for retention window? | 8, 29 | NEW | P2 | Infra | None | Storage class + PVC config. |  | Not Started
51 | 4. OpenShift | Runtime | Airflow Deployment | Scheduler HA, KubernetesExecutor, pod operator design | HA scheduler required for the window? | 18 | NEW | P1 | Infra + Airflow | Medium | Helm values + custom pod templates per task type. |  | Not Started
52 | 4. OpenShift | Runtime | Worker Pod Autoscaling | Autoscaling design sized to the fan-out | Max concurrency before Oracle contention? | 18, 55 | NEW | P1 | Infra | Low | HPA/KEDA config. Requires the measurement from item 55. |  | Not Started
53 | 4. OpenShift | Runtime | Resource Quotas & Priority | Requests/limits, quotas, priority classes for EOD | Does batch preempt other workloads? | 52 | NEW | P2 | Infra | None | Platform config. |  | Not Started
54 | 4. OpenShift | Runtime | Warm-start / Pre-pulled Images | Cold-start mitigation design | Cold start cost vs the 5-min window? | 45, 52 | NEW | P2 | Infra | Low | Image pre-pull / slim images. Measure first. |  | Not Started
55 | 4. OpenShift | Runtime | Oracle Connection Pooling | Pooling design; the real parallelism ceiling | Max sessions DBA will grant? | 13, 52 | NEW | P1 | Python + Infra | Medium | Custom pool management in the ingestion framework. Sets the fan-out ceiling. |  | Not Started
56 | 4. OpenShift | Runtime | Node Placement | Taints/affinity: batch burst vs always-on API | Dedicated nodes for the real-time lane? | 12, 52 | NEW | P2 | Infra | None | Scheduling config. |  | Not Started
57 | 4. OpenShift | Deployment | CI/CD Pipelines | Build, test, scan, promote pipeline design | Pipeline per component or monorepo? | 45, 46 | NEW | P1 | CI/CD | Medium | Custom pipelines: Python unit tests, dbt compile/test in CI against a test schema. |  | Not Started
58 | 4. OpenShift | Deployment | GitOps / ArgoCD | Manifest promotion and drift control | Environment promotion gates? | 44, 57 | NEW | P2 | CI/CD | Low | Standard GitOps config. |  | Not Started
59 | 4. OpenShift | Deployment | dbt Release & Rollback | dbt versioning, release cadence, rollback design | Rollback of an SCD2 dim - how? | 15, 16, 21 | NEW | P1 | dbt + CI/CD | High | No native rollback for a merged SCD2 dim. Custom restore path tied to the replay engine. |  | Not Started
60 | 4. OpenShift | Deployment | Database Change Management | DDL control for RAW/STG2/Gold + PBDW/IMDS | Does Gold sit inside BBH prod change control? (AD-1) | 16, 37 | NEW | P1 | Process + DDL | Low | Process design + migration tooling. |  | Not Started
61 | 4. OpenShift | Deployment | Blue-Green / Canary (API lane) | Zero-downtime release design for real-time | Needed for phase 1 or later? | 12 | NEW | P3 | Infra | None | Platform capability. |  | Not Started
62 | 4. OpenShift | Operations | HA / DR | DR topology, RTO/RPO for the batch window | What is the agreed RTO/RPO? | 44 | NEW | P2 | Infra | Low | Topology design + runbook. |  | Not Started
63 | 4. OpenShift | Operations | Backup & Restore | Airflow metadata DB, config store, quarantine volumes | Restore tested how often? | 33, 50 | NEW | P2 | Infra | None | Backup tooling config. |  | Not Started
64 | 4. OpenShift | Operations | Monitoring Stack | Prometheus/Grafana/log aggregation wired into item 34 | One stack, not a parallel one - confirm | 34 | NEW | P2 | Infra | Low | Dashboards + alert rules. |  | Not Started
65 | 4. OpenShift | Operations | Cost & Capacity Monitoring | Capacity model for a sharply peaked EOD burst | Peak-to-average ratio acceptable? | 52, 53 | NEW | P3 | Infra | None | Tooling config. |  | Not Started
LEGEND / HOW TO USE
Engineers fill in the yellow columns only: Owner (M), Status (N), Target Date (O), Notes (P). Columns A-L are the agreed scope baseline - raise a change request rather than editing them.
Status values: Not Started / In Design / In Review / Approved / Blocked.
Technology: Python ¦ dbt ¦ Airflow ¦ Oracle DDL ¦ Infra ¦ CI/CD ¦ Vendor ¦ Contract ¦ Analysis. Combined values mean the component spans two tracks.
Custom Build: High = bespoke engineering, no framework default covers it (design doc mandatory before code). Medium = framework plus custom macros/operators. Low = mostly configuration. None = no build in this phase.
Source: 'SEI v5' / 'BBH V4.2' = one deck only. 'Both' = agreed. 'Both (conflict)' = decks disagree, read Decisions tab. 'NEW' = in neither deck; scope addition needing approval.
AD-1..AD-12 in Key Design Questions are the open architecture decisions on the Decisions tab. A component citing an open AD cannot be finalised until that AD closes.
Example row: ¦ 13 ¦ 2. Hub ¦ Processing ¦ Python Ingestion Framework ¦ Module design... ¦ ¦ 8, 14, 23 ¦ SEI v5 ¦ P1 ¦ Python ¦ High ¦ CORE BUILD... ¦ A. Sharma ¦ In Design ¦ 2026-09-15 ¦ Framework skeleton drafted ¦

## Decisions
ID | Decision | SEI v5 position | BBH V4.2 position | Consequence if unresolved | Blocks components | Recommendation | Owner | Status
AD-1 | Gold write target: Hub-owned schema vs PBDW/IMDS direct | Gold materialised into existing Oracle DW tables | No Gold layer; Stage 2 feeds consumers | dbt writes production schemas; blast radius and change control shift | 16, 37, 60 | Hub-owned Gold schema that publishes |  | Open
AD-2 | Corrections: in-place merge vs bitemporal append | Merge (update existing) on facts | Bitemporal handling held in Stage 2 | Merge destroys history; breaks as-of restatement and replay | 17, 21, 31, 59 | Bitemporal append with as-of resolution |  | Open
AD-3 | Apigee: firm decision or placeholder | BBH runs an Apigee proxy (two nodes) | Vendor-neutral 'API Gateway / Data Plane' | SEI presumes a BBH decision | 11, 12 | Pin explicitly or correct SEI diagram |  | Open
AD-4 | Intraday: batch pipeline or real-time lane | In scope, identical flow to EOD | Batch lane annotated EOD only | Window sizing and cadence undefined | 12, 20 | Decide one lane; not both |  | Open
AD-5 | Partial batch: halt-all vs per-domain proceed | Not addressed | Not addressed | Undefined behaviour on single-file failure | 18, 22 | Halt-all until measured, then relax |  | Open
AD-6 | Monitoring system of record | SEI Status Dashboard AND Integration360 | Integration360 as cross-cutting capability | Two dashboards, no single truth | 7, 30, 35 | Integration360 as recon system of record |  | Open
AD-7 | Stage 1 ingestion technology | Python (cx_Oracle / SQL*Loader / External Tables) | Arrow labelled dbt | BBH slide is wrong; fix before it is quoted | 13 | DECIDED: Python. Correct BBH slide |  | Open
AD-8 | RAW immutability | Immutable, append only | Source as delivered | - | 14, 21 | DECIDED: immutable append-only |  | Open
AD-9 | DQ gates blocking vs advisory | DQ check drawn after Gold | Recon & error handling, unspecified | Post-Gold check blocks nothing; bad data already published | 23-28 | DECIDED: blocking, with G4 before publish |  | Open
AD-10 | Transport protocol | Unspecified | sFTP reception at Landing Zone | BBH has committed further than SEI | 8, 49 | Confirm sFTP or agree alternative |  | Open
AD-11 | Outbound scope this phase | Fully diagrammed | Absent entirely | Build expectation mismatch | 6, 10, 11 | State in or explicitly out of scope |  | Open
AD-12 | Pivotal in scope | Not in the 8-component inbound list | Named consumer of Stage 2 | Scope gap on the SEI side | 39 | Add to SEI scope or drop |  | Open